FRESHLEAF PROGRAM PROJECT CHARTER

Project Name: FreshLeaf Organic B2B Platform and Consumer App Enhancement Program

Version: 1.0

Date: 04/24/2026

Sponsor: General Director, FreshLeaf

Project Owner: Operations and Marketing Director

Technical Owner: IT Department

1. Project Authorization Statement

This document formally authorizes the FreshLeaf program to execute two coordinated tracks:

Track 1: Organic Vegetable B2B Platform (primary business track).

Track 2: Consumer Mobile App Enhancement (existing app optimization track).

The program manager and designated track leads are authorized to plan and execute approved work using assigned resources and budget.

2. Project Goal and Purpose

FreshLeaf will strengthen organic vegetable commerce by improving B2B operations while sustaining a high-quality consumer digital experience.

Primary goal: enable trusted B2B trade for retailers, restaurants, and resellers with governance, visibility, and repeat ordering capability.

Consumer boundary: the consumer mobile app is already built and remains in scope only for enhancement, reliability, and release quality improvements.

Trust and compliance goal: vendor real-identity registration and admin approval are mandatory before vendor activation.

3. Participants and Roles

Program Sponsor: General Director.

Program Owner: Operations and Marketing Director.

Technical Owner: IT Department / CTO delegate.

Program Manager: Assigned by PMO and engineering leadership.

Track Leads: Mobile Engineering Lead, Admin Web Lead, Vendor Operations Web Lead.

Core Roles: Product design, Flutter engineers, Laravel/API engineers, QA, DevOps/Release, Security and Compliance reviewer.

4. Stakeholders

Business stakeholders: operations, procurement, finance, marketing, customer support.

External stakeholders: business buyers (retailers, restaurants, resellers), approved vendors/farm suppliers.

Governance stakeholders: steering committee, security/compliance reviewers.

5. Requirements and Resource Needs

Platform requirements: secure role-based access for admin, vendor, and user domains.

Operational requirements: onboarding, profile/address management, product visibility, payment methods, wallet transactions, and order-related flows.

Compliance requirements: real legal identity data and verification evidence for vendors; auditable approval and rejection records.

Delivery resources: dedicated cross-functional teams, QA environments, CI pipelines, release tooling, and support runbooks.

Interface note: no new public API contract is introduced by this charter; this charter aligns delivery to existing role-based interfaces.

6. Constraints and Key Risks

Constraints: target launch windows are fixed by business campaign and operations readiness; each track keeps its approved budget envelope.

Risk: identity fraud or incomplete vendor documents. Mitigation: mandatory verification checklist, approval SLA, escalation workflow.

Risk: organic trust and product transparency gaps. Mitigation: required metadata, periodic compliance review, audit logs.

Risk: payment or reconciliation mismatches. Mitigation: wallet/payment traceability and recurring reconciliation checks.

Risk: mobile regression or performance decline. Mitigation: analyze/test/release gates and device coverage testing.

7. Implementation Milestones (Parallel Tracks)

Track 1 - B2B Platform (Admin Web and Vendor Web)

Initiation and Requirements: 03/01/2026 - 03/15/2026

UX/UI Design: 03/15/2026 - 04/06/2026

Development: 04/06/2026 - 05/23/2026

Content and Product Setup: 04/19/2026 - 05/31/2026

Testing: 05/23/2026 - 06/16/2026

Training and Launch Preparation: 06/17/2026 - 06/27/2026

Go-Live and Support: Target 06/30/2026

Track 2 - Consumer Mobile App Enhancement

Project Alignment and Requirements: 04/24/2026 - 05/10/2026

UX Refinement and Technical Planning: 05/11/2026 - 05/31/2026

Core Development (Shopping, Checkout, Profile, Orders): 06/01/2026 - 07/10/2026

Wallet, Payments, and AI Assistant Integration: 06/20/2026 - 07/25/2026

Testing (Functional, UAT, Localization, Performance): 07/15/2026 - 08/05/2026

Release Hardening and Store Preparation: 08/06/2026 - 08/14/2026

Go-Live and Hypercare: Target 08/15/2026

8. Communication Plan

Weekly: track-level planning/review and implementation sync.

Bi-weekly: cross-track steering review for scope, dependencies, and risks.

Monthly: sponsor-level governance update with budget, milestone, and risk status.

Change control: scope additions require formal approval and Phase 2 backlog assignment when deferred.

9. Deliverables

Main charter deliverables: approved scope, milestones, governance model, risk controls, and budget baseline.

Track 1 deliverables: operational admin and vendor web capabilities with verification governance and approval workflow.

Track 2 deliverables: production-ready mobile enhancements across shopping, checkout, wallet/payment, orders, profile, and AI assistant reliability.

Documentation deliverables: architecture notes, release and operations runbooks, and support handover references.

10. Cost Overview

Track 1 - B2B Platform Budget

UX/UI and Discovery: $5,000

Development: $30,000

Content and Product Setup: $5,000

Infrastructure and Tools: $5,000

Contingency: $5,000

Track 1 Total: $50,000

Track 2 - Consumer Mobile Enhancement Budget

Product and UX Design: $8,000

Mobile and Backend Development: $28,000

QA and UAT: $6,000

Infrastructure, Tools, and Distribution: $4,000

Contingency: $4,000

Track 2 Total: $50,000

Program Budget Note: track budgets are managed separately; aggregate reference total is $100,000.

11. Approval and Sign-off

Project Sponsor (General Director): ____________________ Date: __________

Project Owner (Operations and Marketing Director): ____________________ Date: __________

Technical Owner (IT Department / CTO Delegate): ____________________ Date: __________

Appendix A - Mobile App Enhancement Process

A1. Architecture and stack: Flutter with GetX modular feature structure, Dio-based API clients, local persistence, EN/KM localization, and realtime messaging integration.

A2. Feature modules: onboarding/login/register, dashboard/home/search, product list/detail, cart/checkout, orders/order detail, wallet/top-up/payment QR/saved cards, profile/notifications, AI assistant chat.

A3. Process gates: branch-based development, code review, flutter analyze, focused module tests, release build validation, and environment-based build scripts.

A4. Integration focus: API contract stability, authenticated session handling, payment flows, and realtime event delivery quality.

A5. Release output: staged release candidate, UAT sign-off, production rollout, and hypercare monitoring.

Appendix B - Admin Web App Development Process

B1. Platform: Filament admin panel at /admin with authenticated access and role-aware operations.

B2. Operational modules: users, vendors, products, product categories, orders, purchase orders, suppliers, units, inventory batches, wallets, and wallet transactions.

B3. Governance modules: admin settings pages (profile, security, application settings) and dashboard widgets for operational oversight.

B4. Vendor control workflow: admin review of vendor submissions with explicit approve/reject actions and auditable decision metadata.

B5. Quality and release: resource-level validation, policy and middleware checks, regression testing of critical operations, and deployment runbook execution.

Appendix C - Vendor Web App Development Process

C1. Platform: Filament vendor panel at /vendor with login/registration and vendor-specific settings pages.

C2. Vendor settings workflow: profile, business profile, financial details, security, and verification document management.

C3. Verification process: vendor uploads identity and store evidence; edits are locked after verification; admin approval remains mandatory for operational activation.

C4. Operational integration: vendor APIs for profile, addresses, product visibility, and wallet/history interactions.

C5. Quality and release: verification flow testing, permission and route-guard testing, and operational readiness checklist before release.

Reference Note

This charter format follows project-charter principles for concise authorization and high-level control, with detailed execution process retained in appendices.