PROJECT CHARTER
Project Name: FreshLeaf Mobile Application
Version: 1.0
Date: 04/24/2026
Sponsor: FreshLeaf Executive Sponsor
Project Owner: Product Management
Technical Owner: Mobile Engineering Team

1. Purpose and Background

FreshLeaf requires a stable, scalable, and user-friendly mobile app to:

- Provide a complete digital grocery journey for customers from discovery to delivery.

- Strengthen FreshLeaf brand trust with a modern and localized mobile experience.

- Consolidate shopping, ordering, payments, wallet, and support into one platform.

The current state includes fragmented experiences and manual support overhead, reducing conversion, retention, and operational efficiency.

2. Objectives

Business Objectives

- Increase completed checkout conversion by 15% within 6 months of release.

- Increase monthly active users by 20% within 12 months.

- Reduce payment and order support tickets by 25% within 6 months.

Technical Objectives

- Deliver a responsive and reliable Flutter app for Android and iOS.

- Implement modular GetX architecture and maintainable code standards for rapid feature delivery.

3. Scope

In Scope

- Core User Experience

  - Authentication, onboarding, dashboard navigation, and profile management.

  - Shopping flow: home, search, product list/detail, cart, and checkout.

  - Order lifecycle: order list, order detail, and status visibility.

- Payments and Wallet

  - Wallet balance, top-up flow, payment method selection, and payment QR flow.

  - Secure payment session handling and card-based saved payment methods.

  - Order verification protection with optional PIN security workflow.

- Platform and Services

  - API integration using Dio and typed API response parsing.

  - Realtime AI assistant messaging integration with REST + private channels.

  - Local persistence for auth/session preferences and chat history.

  - Localization support for English and Khmer.

- Non-functional

  - Security controls for token storage, permission handling, and authenticated routes.

  - Performance, accessibility, and monitoring readiness for production usage.

- Release and Operations

  - Build scripts for environment-based APK/App Bundle generation.

  - CI-compatible lint/analyze/test workflow for quality gates.

  - Documentation for setup, release, and secure configuration practices.

Out of Scope (Phase 1)

- Native desktop and web versions.

- Complex ERP/SIS enterprise integrations beyond current API endpoints.

- Multi-vendor marketplace management features.

4. Key Deliverables

- Production-ready FreshLeaf mobile app modules aligned to product scope.

- Fully functional flows for auth, shopping, checkout, orders, wallet, and profile.

- AI assistant chat experience with realtime updates and persisted sessions.

- Localization and theme support for consistent EN/KM user experience.

  - Core screens for onboarding, home, product, cart, checkout, orders, wallet, and profile.

- Technical documentation:

  - Architecture overview, run/build guides, secure config setup, and support notes.

- Quality baseline using analyze and test execution workflows.

5. Stakeholders and Roles

- Project Sponsor: FreshLeaf Executive Sponsor

- Steering Committee: Sponsor, Product Lead, Engineering Lead, Operations Lead

- Project Owner (Business): Product Management

- Technical Owner: Mobile Engineering Lead

- Project Manager: Assigned by product and engineering leadership

Core Technical Team

- Product Designer

- Flutter Front-end Engineers

- Backend/API Engineers

- Content and Localization Owner

- QA Engineer

- DevOps/Release Engineer

Key Stakeholders

- Customer Support Team

- Business Operations

- IT and Security

- Marketing and Growth

- Finance/Payments Team

- Representative customer users

6. Assumptions and Constraints

Assumptions

- Required API endpoints and authentication services remain available and stable.

- Product, design, and localization reviews are delivered on agreed sprint timelines.

- Release credentials, certificates, and store assets are available before launch.

Constraints

- Target release aligned with business campaign window (target: 08/15/2026).

- Delivery must stay within approved team capacity and budget limits.

- Compliance with security, data protection, and app store policies is mandatory.

7. Milestones and High-Level Timeline

- Project Alignment and Requirements: 04/24/2026 - 05/10/2026

- UX Refinement and Technical Planning: 05/11/2026 - 05/31/2026

- Core Development (Shopping, Checkout, Profile, Orders): 06/01/2026 - 07/10/2026

- Wallet, Payments, and AI Assistant Integration: 06/20/2026 - 07/25/2026

- Testing (Functional, UAT, Localization, Performance): 07/15/2026 - 08/05/2026

- Release Hardening and Store Preparation: 08/06/2026 - 08/14/2026

- Go-Live and Hypercare: Target 08/15/2026

8. Risks and Mitigations

- API instability or backend contract changes

  - Use typed response parsing, contract validation, and release branch freeze windows.

- Scope creep across feature modules

  - Apply sprint-level change control and prioritize Phase 2 backlog items.

- Payment or permission flow regressions

  - Add focused regression tests and QA checklist before each release candidate.

- Performance issues on lower-end devices

  - Optimize UI rendering, network payload usage, and image handling patterns.

- Resource contention across parallel features

  - Sequence milestones with clear ownership and weekly dependency reviews.

9. Budget Overview (High Level)

- Product and UX Design: $8,000

- Mobile and Backend Development: $28,000

- QA and UAT: $6,000

- Infrastructure, Tools, and Distribution: $4,000

- Contingency: $4,000

Total: $50,000

10. Governance and Change Control

- Weekly sprint planning/review and cross-functional status sync.

- Bi-weekly steering review for scope, risks, and release readiness.

12. Approvals

Project Sponsor (FreshLeaf Executive Sponsor): ____________________ Date: __________

Project Owner (Product Management): ____________________ Date: __________

Technical Owner (Mobile Engineering Lead): ____________________ Date: __________